## Version
EdgeConnect Work Log 4-May-2017
EdgeConnect Europe

## Closed
# | Impact | Priority | Account Source | Requirement / Issues To Be Addressed | Comments | Status | Owner | Start Date | End Date | Planned Release Date | RAGB | Next Steps/Comment
1 |  |  | Experian | Click on alarm button -> detailed page -> Top right corner -> Icon (escalate), home page layout scroll to |  | Closed | Dev Team | Mar 1st | Mar 3rd | Mar 3rd |  | Completed
2 |  |  | Experian | Click on alarm button -> select a notification -> Details Page -> click back, takes to home page instead on notification page |  | Closed | Dev Team | Mar 1st | Mar 3rd | Mar 3rd |  | Completed
3 |  |  | Experian | Bottom layout to be reduced (height between Bundle 3 & Bottom Screen) |  | Closed | Dev Team | Mar 1st | Mar 3rd | Mar 3rd |  | Completed
4 |  |  | Experian | Hold loading indicator till data load completes -Loader and sorry text |  | Closed | Dev Team | Mar 1st | Mar 3rd | Mar 3rd |  | Completed
5 |  |  | Experian | Load data based on the category clicked (other data to be neglected) (KT, FS,BS,Cutover) |  | Closed | Dev Team | Mar 1st | Mar 3rd | Mar 3rd |  | Completed
6 |  |  | Experian | Milestones: After clicking on create , half page appears with previous page & disappears (Dashboard going to bottom) |  | Closed | Dev Team | Mar 1st | Mar 3rd | Mar 3rd |  | Completed
7 |  |  | Experian | Milestones: After create function , coming back to home screen, bundle layout scrolls below & cannot scroll up |  | Closed | Dev Team | Mar 1st | Mar 3rd | Mar 3rd |  | Completed
8 |  |  | Experian | Executive Updates: Click on team distribution-> Detailed Page -> click on top right icon (escalate) - > burger menu(dashboard) -> layout rearranges (Dashboard going to bottom |  | Closed | Dev Team | Mar 1st | Mar 3rd | Mar 3rd |  | Completed
9 |  |  | Experian | Exec Dashboard Charts: Overall Progress % Update By Bundle: Already there |  | Closed | Dev Team | Mar 1st | Mar 2nd | Mar 2nd |  | Completed
10 |  |  | Experian | Exec Dashboard Charts: % Complete KT Sessions By Bundle (actual vs planned) Bar Chart: |  | Closed | Dev Team | Mar 1st | Mar 2nd | Mar 2nd |  | Completed
11 |  |  | Experian | Exec Dashboard Charts: Risks By Bundle Bar Chart: Remove for now |  | Closed | Dev Team | Mar 1st | Mar 2nd | Mar 2nd |  | Completed
12 |  |  | Experian | Project Dashboard: Overall Progress % Update By Bundle: Already there |  | Closed | Dev Team | Mar 1st | Mar 2nd | Mar 2nd |  | Completed
13 |  |  | Experian | Project Dashboard: % Complete KT Sessions By Bundle (actual vs planned) Bar Chart: |  | Closed | Dev Team | Mar 1st | Mar 2nd | Mar 2nd |  | Completed
14 |  |  | Experian | Project Dashboard: Risks By Bundle Bar Chart: Remove for now |  | Closed | Dev Team | Mar 1st | Mar 2nd | Mar 2nd |  | Completed
15 | HIGH | 1 | Experian | Mile Stones: Project(tab) - > data load to be faster |  | Closed | Experian Team | Mar 8th | Mar 3rd | Mar 3rd |  | Dev Team: Fixed please check and confirm
16 | MED | 2 | Experian | Actual end date should be an optional field. It by default saves a 1970 date if user tries to remove it or leaves it blank | The workaround is to enter the same date as the planned end date | Closed | Experian Team | Mar 1st | Mar 3rd | Mar 3rd |  | Dev Team: Fixed please check and confirm
17 | MED | 2 | Experian | Mile Stones: Click on the create button -> submenu doesn’t pop with drop down |  | Closed | Experian Team | Mar 1st | Mar 3rd | Mar 3rd |  | Dev Team: Dropdowns will be populated as per the level of selection
18 | MED | 2 | Experian | Portal Account Admin User :This will enable coverage for when the owner is unavailable |  | Closed | Experian Team |  |  | Mar 3rd |  | Dev Team: We have an admin USER for Experian who can login to portal and manage the data Experian: Experian-admin/Experian$123
19 | LOW | 3 | Experian | Milestones: Create button response is too slow |  | Closed | Experian Team | Mar 8th | Mar 3rd | Mar 3rd |  | Dev Team: Fixed please check and confirm
20 | LOW | 3 | Experian | Mile Stones: Flags menu, Navigation menu takes time to load |  | Closed | Experian Team | Mar 8th | Mar 3rd | Mar 3rd |  | Completed
21 | HIGH | 1 | Experian | Bar charts - the % complete number is only partially showing when the % complete is low |  | Closed | Dev Team | Mar 14th | Mar 16th | Mar 17th |  | Dev Team: Development Completed
22 | HIGH | 1 | Experian | Milestones: Remove background image on data loading pages (white background is preferred ) with loading indicator Loader and sorry text | Experian Team: We need to completely remove the "cloud" image across the app and leave it as a blank page only | Closed | Dev Team | Mar 1st | Mar 16th | Mar 17th |  | Dev Team: Image will be removed
23 | HIGH | 1 | Experian | Executive Updates: Remove NA legend for the bar charts |  | Closed | Dev Team | Mar 1st | Mar 14th | Mar 17th |  | Dev Team: Development Completed
24 | HIGH | 1 | Experian | Executive Updates: Updates (tab) -> image to be removed so only blank page appears if there are no updates |  | Closed | Dev Team | Mar 8th | Mar 16th | Mar 17th |  | Dev Team: New image will be introduced
25 | HIGH | 1 | Experian | Change dates to UK format -APP | Dev Team: Common format will be used that will be acceptable as the application is used by different accounts in different countries Dev Team: Y axis of Bar chart can be updated through Portal | Closed | Dev Team | Feb 22nd | Mar 14th | Mar 17th |  | Dev Team : Development in Progress
26 | MED | 2 | Experian | If any of the identified date, due date or actual start date is updated with a date, it actually saves the next day's date |  | Closed | Dev Team | Mar 8th | Mar 16th | Mar 17th |  | Dev Team: Need to be clear that this is within the portal and not the App
27 | LOW | 3 | Experian | Exec Dashboard Liquid Chart % Rounding When entering %’s to one decimal place in the portal the app does not rounding correctly |  | Closed | Dev Team | Mar 10th | Mar 16th | Mar 17th |  | Dev Team : Development in Progress
28 | LOW | 2 | Experian | Add Refresh Button – To check updates made you currently have to log out of the app and then back in | Dev Team: Refresh button will be introduced Stuart : Refresh button should be relocated | Closed | Dev Team | Mar 10th | Mar 16th | Mar 17th |  | Dev Team : Development in Progress
29 | HIGH | 2 | Experian | Menu: Click on search -> click on setting icon (keyboard doesn’t appear |  | Closed | Dev Team |  | Mar 30th | Mar 31st |  | 21/04 Stuart: This all looks OK and so can be closed
30 | HIGH | 2 | Experian | Logging & Monitoring – Full audit trails of user activity required, this includes activity by UST within the application such as privileged user activity | Experian Team: Reference to security audit - we have 90 days | Closed | Dev Team | Mar 10th | Mar 30th | Mar 31st |  | Completed Logging. On request data can be pulled and shared as CSV file 07/04 Stuart: Stuart requested consoldidated table / report of all the security audit remediation actions with a status update so this can be shared with Experian before closing 12/04 Stuart: George shared the log with Stuart who in turn shared with Mike
31 | HIGH | 2 | Experian | User Authentication – password requirements not met | Experian Team: Reference to security audit - we have 90 days | Closed | Dev Team | Mar 10th | Mar 30th | Mar 31st |  | • Server credentials security implemented • The application must force the initial and reset passwords that are set by administrators to be changed immediately upon first use. • The application must lock user accounts after no more than 5 consecutive incorrect login attempts. They must be locked out for a minimum of 30 minutes or until an administrator re-enables the user account. • Implemented new password policy • Force normal user to change the password in 90 days, and admins in 30 days. 7/04 Stuart: Stuart requested consoldidated table / report of all the security audit remediation actions with a status update so this can be shared with Experian before closing
32 | HIGH | 1 | Experian | Disable adding risks/issues from the mobile application | Dev Team: Team analyzing on the feasibility of disabling for Experian | Closed | Dev Team | Mar 8th | Mar 30th | Mar 31st |  | Admin can disable create & edit of Issues/Risks/Milestone or the entire module from app 21/04 Stuart: I can confirm this can be marked as complete
33 | HIGH | 2 | Experian | User Registration – passwords to the systems sent via email | Experian Team: Reference to security audit - we have 90 days | Closed | Dev Team | Mar 10th | Mar 30th | Mar 31st |  | 07/04 Stuart: Stuart requested consoldidated table / report of all the security audit remediation actions with a status update so this can be shared with Experian before closing
34 | HIGH | 2 | Team | Reduce the font size in overall update pages (Giving priority to bar chart, liquid chart, doughnut chart) |  | Closed | Dev Team | Mar 27th | Mar 30th | Mar 31st |  | 21/04 Stuart: This all looks OK and so can be closed
35 | MED | 3 | Team | Utilize top space to display title in details page appropriately |  | Closed | Dev Team | Mar 27th | Mar 30th | Mar 31st |  | 21/04 Stuart: Please clarify the issue and fix 24/4 George : This was not a issue. The top space of the title was reduces to give more space for the detail area
36 | MED | 3 | Team | Liquid charts label wrapping to be done in listing page, limit to three. |  | Closed | Dev Team | Mar 27th | Mar 30th | Mar 31st |  | 21/04 Stuart: Please clarify the issue and fix 24/4 George : When the number of liquid charts where more than 3, in summary sheet the layou was breacking. So restricted the number of charts to be shown in summary to 3. In detailed screen we could see all charts
37 | HIGH | 2 | Team | Legend in bar charts should be placed above or below accordingly, avoid overlapping |  | Closed | Dev Team | Mar 27th | Mar 30th | Mar 31st |  | 21/04 Stuart: Legend don't appear to have been changed / moved?
38 | HIGH | 2 | Experian | No need to display ‘0’ if value is ‘00’ in bar chart |  | Closed | Dev Team | Mar 27th | Mar 30th | Mar 31st |  | 21/04 Stuart: This all looks OK and so can be closed
39 | MED | 2 | Experian | Bar chart % complete overlap issue |  | Closed | Dev Team | Mar 27th | Mar 30th | Mar 31st |  | 21/04 Stuart: This all looks OK and so can be closed
40 | MED | 2 | Experian | Remove refresh button from dashboard view |  | Closed | Dev Team | Mar 27th | Mar 30th | Mar 31st |  | 21/04 Stuart: This all looks OK and so can be closed
41 | HIGH | 2 | Experian | Introduce Burndown charts feature |  | Closed | Dev Team | Mar 23rd |  | Apr 7th |  | Development is in Progress 10/04 Stuart: Is the y axis limited to a set range? Anything over 90 KT sessions doesn’t appear to work. Shared screen shot with George and team 21/04 Stuart: Tried to recreate a burndown chart but the graph doesn't appear to now reflect the burndown data correctly. Sent email to George and team with screen shots 24/4 George: Will check the same 02/05 Stuart: When testing in production, the first screen labels are incorrect and appear to be reflecting the legend labels rather than the description entered. Currently it is showing "Actual" and "Ideal"
42 | Med | 2 | Experian | Relocate refresh button from dashboard (temporarily removed ref #41) |  | Closed | Dev Team | Apr 3rd |  | Apr 7th |  | 21/04 Stuart: This all looks OK and so can be closed
43 | HIGH | 2 | Experian | Weighted average calculation |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: This all looks OK and so can be closed
44 | MED | 2 | Experian | Change labelling Identified date to Planned Start date and Due Date to Planned End Date |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: This all looks OK and so can be closed
45 | MED | 2 | Experian | Milestone date in transition Card is offset to 1 day |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: This all looks OK and so can be closed
46 | MED | 2 | Experian | Extend disabling the provision to comment, message and escalate. At a later date Experian are likely to enable some / all of these features |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: Message, Comments and Flag disable functionality tested and seems to work and so can be closed
47 | MED | 2 | Experian | Actual start date to be populated in the flash card if atleast 1 of its tasks has date entered |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: This all looks OK and so can be closed
48 | Med | 3 | Team | Send email on forgot password option |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: This all looks OK and so can be closed however it did then take me straight to the web portal once I'd reset my password
49 | Med | 3 | Team | Notification on app updates |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: Not yet seen this
50 | Med | 3 | Team | Resend password expiration link |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: Unable to test
51 | Med | 3 | Team | Delete option for chart updates by admin/creator |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: This all looks OK and so can be closed
52 | MED | 2 | Team | Grouping of Executive updates by levels |  | Closed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: This all looks OK and so can be closed
53 |  |  | Hiscox | Srinivasan Jayaraman name is not coming in the risk owner list | [23-Mar:Rijad]:Srinivasan Jayaraman is an Engagement level user and will be available only in Engagement level Risk owner list | Closed
54 |  |  | Hiscox | Milestone is not displayed which was provided earlier through template | [23-Mar:Shihab]: Added in the tracker [23-Mar:Rijad]:We didn’t add Milestone since Assigned to field was blank. Please share the details. We will create the data | Closed
55 |  |  | Hiscox | Project name is not coming in the milestone entry page | [23-Mar:Shihab]: Its mentioned in the sheet already. Not sure which one you are referring to [23-Mar:Rijad]:Project details was not there in the sheet which you provided. So we didn’t create any. Please share the project data | Closed
56 |  |  | Hiscox | I added risk in project tab, but it displays in portfolio tab | [23-Mar:Shihab]: If project is not available,then we should stop user to enter risk. [23-Mar:Rijad]:You cannot add Risk under project tab since we didn’t created any project. | Closed
57 |  |  | Hiscox | Project and Portfolio is not as per the given data | [23-Mar:Shihab]: Portfolio is coming as Phoenix in risk form which is wrong. [23-Mar:Rijad]:This is as per the shared data | Closed
58 |  |  | Hiscox | Updated about me section with details, but while submitting it, no success/failure message found. While coming back to the screen all entered data was lost. | [23-Mar:Rijad]: It is showing a toast message “User profile updated successfully” | Closed
59 |  |  | Hiscox | No project is visible in my login. User guide doesn’t explain how to create project. Hope this pulls from the Optimus DB directly by app. | [23-Mar:Shihab]: Its mentioned in the sheet already. Not sure which one you are referring to [23-Mar:Rijad]:Projects were not added since no data was shared. Currently project is not pulling from Optimus DB. We have a web version and we will be adding those details from web. | Closed
60 |  |  | Hiscox | It will be good if we have the details on which are the section user need to enter through app with hierarchy | [23-Mar:Rijad]:User cannot create Executive updates, User and Organization details from Mobile app. These details can be created only from web. | Closed
61 |  |  | Hiscox | My team is not updated as per the team structure | As per the design we displays only manger and the drirect reportees only, Currently you are not a manger or a reportee to any manager. | Closed
62 |  |  | Hiscox | If we have 2 details mentioned in liquid chart, it is not displaying correctly in mobile app | [4-May:Shihab]: It is working fine now in mobile [2-May:Rijad]: need more clarity on this. | Closed
63 |  |  | Hiscox | Created a phase, but not able to map milestone | [5-May:Rijad]: Discussed in meeting, its working. | Closed
64 | MED | 2 | Experian | Menu: Click on search ->click on setting icon -> click on menu button -> click on slide over arrow(keyboard stays in all the screens |  | Closed | Dev Team | Mar 27th | Mar 30th | Mar 31st |  | 21/04 Stuart: I've clicked on the settings (cog) and then the hamburger button. This takes me back to the home screen and the key board pops up. The only way to remove it is to click on another menu option eg Dash Boards 12/5 George : Not able to replicate 12/05 Stuart: Looks to be an iPhone 5S issue so can close
65 | MED | 2 | Experian | Add a risk category to capture if a risk is accepted or if there is a mitigation plan in place |  | Completed | Dev Team |  |  | Apr 21st |  | 12/5 George: Metigation plan is available in APP. Demo given to Stuart on how to do the same. Option to Edit Metigation plan from Web will be released on 19/5 12/05 Stuart: Confirmed ability to change the status and add mitigation plan details through the app as a one-off activity. Once set, the status or plan details cannot be changed. Through the portal can currently only change the status. Per George's comments the plan needs to be editable thorugh the portal then this can be closed
66 |  |  | Hiscox | Required ITERATION menu in website to add iteration details | [2-May:Rijad]: Enabled Phases for Hiscox, We can't rename it to Iteration. | Discard |  |  |  | TBD
67 |  |  | Hiscox | Not able to edit category ( to change from project level to engagement level) | [4-May:Shihab]: Can you make it editable? [2-May:Rijad]: As per the design once you create you will not be able to change the level. | Discard
68 | MED | 2 | Experian | Executive Updates: Experian KT - > detailed view -> color differentiator (NA, burned outage, planned) - To be left aligned |  | Closed | Dev Team |  |  | TBD |  | Dev Team: Consulting with UI team 12/05 Stuart: I am unsure of the issue and everything looks OK. Happy to mark as closed / delete the record unless anyone is aware of an issue and can re-word / resolve
69 | MED | 2 | Experian | Edit option for Admin in Executive updates screen |  | Closed | Dev Team |  |  | TBD |  | Dev Team: Feasibility study in progress 12/05 Stuart: Please clarify the requirement - this reads as allowing the Admin user to edit Exec charts through the portal no matter who's creeated them? The Admin should be able to edit any charts or data in the portal for the respective account no matter which user created the charts / data
70 | LOW | 3 | Experian | Home Screen: Previous launched screen reopens during launch |  | Closed | Dev Team |  |  | TBD |  | Dev team :More clarification required 12/05 Stuart: Whenever I go back the app or log out and log back in I am taken to the Dashboard screen. The requirement should be that the user is taken back to the last screen they were in
71 | LOW | 3 | Experian | Milestones: Title getting cut |  | Closed | Dev Team |  |  | TBD |  | Stuart 12/05: Example on the Milestones / Project view: "Bundle 1b - App Service - Knowledge Transfer" milestone group header reads "Bundle 1b - App Service - Knowledge Tran..." I'm not sure where this heading is maintained to help make a recommendation
72 |  |  | Hiscox | Can you explain what is weigtage in phase? Can we remove that ? | [5-May:Rijad]: All the phases of project may not be similar, eg: if you have 4 phases and Knowledge Transfer(KT), Forwared Shadow, Reverse Shadow, and Service CutOver. if you have completed the KT and no other phases are started then the overall project status will be 25%. Sometimes the KT will be having only 10% of overall project status, that you can do by updating the weightage, so the overall % will be 10% NB: BY default the weightage is caluclated by Number of phases/100 | Closed
73 |  |  | Hiscox | Can we have phases column created dynamically with our requirement? | [5-May:Rijad]: No the phases are created by manuall now, we can discuss about the dynamic creation. | Open
74 |  |  | Hiscox | Phases created,but when coming back to that menu we have to select engagement, portfolio and then click on view to see the phase which we added. This should be viewed directly when we click on phases. | [5-May:Rijad]: The Buisiness logic is a user can be added multiple to multple projects.So he need to choose the portfolio and project, Your comment copied to our back log. | Open
75 | HIGH | 2 | Experian | Introduce Burndown charts feature |  | Completed | Dev Team | Mar 23rd |  | Apr 7th |  | Development is in Progress 10/04 Stuart: Is the y axis limited to a set range? Anything over 90 KT sessions doesn’t appear to work. Shared screen shot with George and team 21/04 Stuart: Tried to recreate a burndown chart but the graph doesn't appear to now reflect the burndown data correctly. Sent email to George and team with screen shots 24/4 George: Will check the same 02/05 Stuart: When testing in production, the first screen labels are incorrect and appear to be reflecting the legend labels rather than the description entered. Currently it is showing "Actual" and "Ideal" 12/05 Stuart: Retested now some changes have been made. y axis range issues is resolved and legend labling is correct. Only minor outstanding point is when the final planned number reaches 0 and actual numbers continue (overrun) then the planned number doesn't show as 0 on the graph? 8/6 George : Fix for the same is added in todays build
76 | MED | 2 | Experian | How is the dashboard progress status derived? We have examples where the start date is in the future but we’re reporting “In Progress" |  | Completed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: It looks like where the milestone date is in the future we now show "NEW" rather than "In Progress" however we should report "Not Started" - "In Progress" - "Complete" as the status based off the milestone status 12/5 George: Change will be released on 19/5 8/6 George : Please test the same
77 | LOW | 3 | Experian | If there is a risk mitigation plan either add comments or provide link back to the risk log itself |  | Completed | Dev Team |  |  | Apr 21st |  | 02/05 Stuart: The Risk status can now be Open, Accept, Mitigate, Mitigate and Close, Accepted and Close so this is fine. However unsure if Mitgate is selected how to add details for the Mitigation Plan field 12/5 George: Metigation plan is available in APP. Demo given to Stuart on how to do the same. Option to Edit Metigation plan from Web will be released on 19/5 8/6 George : Please test the same
78 |  |  | Hiscox | If we have 2 details mentioned in liquid chart, it is not displaying correctly in mobile app |  | Completed | Dev Team |  |  | 2017-05-19 |  | 8/6 george : Please test the same
79 | MED | 2 | Hiscox | In executive summary added line chart. But displaying incorrectly | [4-May:Shihab]: Please see the attachment 1 in annexure sheet [5-May:Rijad]: Dev team is checking on this. | Completed
80 | MED | 2 | Team | New Design for Login, Issues, Risks, Milestones and detail pages |  | Completed
81 | MED | 2 | Team | New chart with Chartists |  | Completed
82 | MED | 2 | Team | Newly Included comments details page for more comments |  | Completed
2 | Med | 2 | Experian | Colour of Bar chart to be changed from Red |  | Completed | Dev Team |  |  | June 23rd |  | George : Planned for June 23rd release
3 | Med | 2 | Experian | Lost all the capitalisation on all the milestones. CAIS is now Cais, NTT is now Ntt, Experian is now experian, UST is ust etc. |  | Completed | Dev Team |  |  | June 23rd |  | George : Planned for June 23rd release
4 |  |  | Experian | Milestone create / options configuration selected it appears that we can do so through the app |  | Completed | Dev Team |  |  | June 23rd |  | George : Planned for June 23rd release
6 | LOW | 3 | Experian | Dashboard % Complete Mis-Alignment - with the decimal place the % sign is mis-aligned. We should keep to 0 decimal places here |  | Open | Dev Team |  |  | TBD |  | Dev Team: Feasibility study in progress 12/05 Stuart: Please raise the priority on this
8 |  |  | Hiscox | In About me page, there is no description about the text field which we require to enter and submit. | [23-Mar:Shihab]: Suggest to have a placeholder on top of each text which have focus and remove it once the focus is removed [23-Mar:Rijad]:We’ve used placeholder, if any value exist the placeholder will be hidden | Closed |  |  |  | TBD
9 |  |  | Hiscox | Date picker is not working in milestone tracker using mouse in chrome | [2-May:Rijad]: Noted, anyway you can get the datepicker on clicking the arrow next to each field | Closed
10 |  |  | Hiscox | It will be good to have descriptions on what need to enter especially in text fields | [2-May:Rijad]: All the text field has placeholders in place, we've noted the comment will add it. | Closed
11 |  |  | Hiscox | Not able to understand the value 2 and value 3 in bar chart | [2-May:Rijad]: Noted will discuss with Architect, It meant to legends. | Closed
12 |  |  | Hiscox | Serial Number is blank when I have one phases | [5-May:Rijad]: Dev team is checking on this. | Closed
13 |  |  | Hiscox | We can see dashboard in mobile, but nothing in website | [5-May:Rijad]: The dashboard in web is under development, it will availble with web Version2 | Closed
Note on C1: Stuart Saunders (UST, GBR): 1 = High

## Pivot
Count of # | Column Labels
Row Labels | On Hold | To be Confirmed by Account POC | Inprogress - IT4 | Grand Total
Boots |  | 1 |  | 1
DEBENHAMS | 2 |  | 3 | 5
Experian | 4 |  | 1 | 5
Harrods |  |  | 1 | 1
Hiscox | 7 |  | 1 | 8
Provident | 1 |  |  | 1
Schroders |  |  | 1 | 1
Grand Total | 14 | 1 | 7 | 22

## EdgeConnect-Work
# | Impact | Priority | Account Source | Requirement / Issues To Be Addressed | Comments | Required to be fixed before client demo? | Status | Owner | Start Date | End Date | Planned Release Date | RAGB | Next Steps/Comment
1 | LOW | 2 | Experian | Change dates to UK format - Web | Dev Team: Common format will be used that will be acceptable as the application is used by different accounts in different countries |  | Completed | Dev Team |  |  |  |  | 02/05 Stuart: For a Portfolio milestone I updated the date from the calendar but it still appears in US format? Also tried keying in DD MMM YY and managed to save but when checking back date has reverted to original date 12/5 George : Currently apart from date pickers all other date columns are corrected. For Date pickers the change will be relected in Web 2 which is planned for 2/6 release 8/6 George : This will be in place once web2 is live
2 | LOW | 2 | Experian | Burndown Chart Format Updates | • The line is not fluid; burndown charts need to be smooth • It would be better if the x axis labels are in line with the data points • The planned line is red a colour we should avoid |  | Completed | Dev Team |  |  |  |  | 11/09 Stuart: The x axis dates are not formatted correctly as they overlap. Suggest if we're short on space to reduce how many dates are displayed eg show every other week
3 |  |  | Experian | Increase the number of transition phases from 4 in the dashboard | Increase to 5 |  | Completed | [5 empty] | 11/09 Stuart: Confirmed number of phases visible on the dashboard has increased to 5. This can be closed
4 |  |  | Experian | Enable dashboards for any type of project engagement | Analysis in Progress |  | Completed | [5 empty] | 11/09: How are dashboards enabled?
5 | MED | 2 | Experian | Issue / Risk is not editable at Milestone level. |  |  | Completed | Dev Team
6 |  |  | Provident | Highlight Title and Highlight description doesn’t make any sense. We need the purpose of these fields and also make them non-mandatory |  |  | Completed | [5 empty] | 11/9 George : The field is already non mandatory in web 2. Highlight Decription is an area where we can give brief highlight. This appears as the bullet points in detail page
7 |  |  | Schroders | 1. Upon logging in, the first portfolio is displayed under Schroders engagement even if the user is not a member of that |  |  | Completed | [5 empty] | 11/9: Completed in 8/9 release
8 |  |  | Schroders | 2. Labels are not displayed in the bar graphs |  |  | Completed | [5 empty] | 11/9: Completed in 8/9 release
9 |  |  | Hermes |  Mandatory fields need to be marked with asterisks. E.g.: Create User option has many fields but some are not mandatory. These need to be marked out |  |  | Completed | [5 empty] | 11/9: Completed in 8/9 release
10 |  |  | Harrods | • Bar Chart – Project name not displayed completely and getting override along with the chart (sample below 2nd image) |  |  | Completed | [5 empty] | 11/9: Completed in 8/9 release
11 |  |  | Harrods | • Execution Updates – What is the max character we can give in Highlight Description? We are able to give only two bullet points with maximum 250 characters. |  |  | Completed | [5 empty] | 11/9: Completed in 8/9 release
12 |  |  | Hermes | 2) Not able to add table formats in executive updates |  |  | Completed |  |  |  | 29th Sep
13 |  |  | Hermes |  We need to have copy paste facility and import/export from excel and ppt. As this is not supported now, it is causing duplicate effort to again key in all data manually. |  |  | Completed |  |  |  | 29th Sep |  | 11/9 George: Option to Copy Chart/Table from Excel
14 | LOW | 2 | Experian | Bar charts: the gaps / spacing between each bar is too big |  |  | Completed | Dev Team |  |  | 29th Sep
15 |  |  | Experian | Retain milestones on EdgeConnect even if they are closed in the web portal | New state "Archive" will be added and mobile will show all Closed milestones also but not archived once |  | Completed |  |  |  | 29th Sep
16 |  |  | Schroders | 1. The negative axis for a bar graph is missing giving a wrong interpretation of data |  |  | Completed
17 |  |  | Schroders | 1. If values for multiple months are given in a bar graph, while viewing in mobile device, the spacing between the graph is considerably big and the user has to scroll multiple times just to view 6 months of data |  |  | Completed
18 |  |  | Schroders | 2. If data has been loaded for multiple months then viewing of data based on time period is not available i.e. you can only view one set of values which has been published and not the entire set of values available which could help in comparative analysis. A time period based data viewing will be really appreciable. |  |  | Inprogress - IT4 | Midhun
19 |  |  | Hermes | 1) While doing a pie chart , we now need to feed in percentages manually. |  |  | Completed
20 |  |  | Hermes | Charts:  I could not draw the control limit lines and the call out. (red marked oval call out) |  |  | Completed
21 |  |  | Hermes |  Tool tips need to be added for fields, o e.g.: there are different fields for title, Highlight title etc. for bar chart, but what is the significance or difference is not understood. Create User panel also has Name, username etc. |  |  | Completed
22 |  |  | Harrods | • Bar Chart – Currently we can enter only 3 values #Total TCs, #Passed & #Failed and the other values like Not Run, Blocked, In Progress cannot be entered. (sample below 1st image). |  |  | Inprogress - IT4 | [5 empty] | 11/9: Chacking for option to extend till 5
23 |  |  | Provident | Risks - We don’t have the required fields to show risks. Rather than title and description, we need relevant fields to talk about a risk. Optimust screenshot here. Not every detail may be required, but basic risk elements need to be there. These business requirements should be coming to Edge Connect team from SEPG to make this tool more effective. |  |  | On Hold | Swamy
24 | High | 2 | Boots | The updated date is showing up wrong in the mobile view. The create date is shown instead. |  |  | To be Confirmed by Account POC
25 | LOW | 3 | Experian | Escalation capability | Enable notification for Escalation capability Not required currently for Experian |  | On Hold | George/Ajith
26 | LOW | 3 | Experian | Notification feature when a new comment is added anywhere in the application | Not required currently for Experian |  | On Hold | George/Ajith
27 | LOW | 3 | Experian | Can we indicate the number of open messages on the ICON of the app | Not enabling messages and escalations for Experian |  | On Hold | George/Ajith
28 | LOW | 3 | Experian | Can we indicate the number of open messages on the ICON of the app | Not enabling messages and escalations for Experian |  | Inprogress - IT4 | George/Ajith
29 | LOW | 3 | Experian | Change Engagement header to “Experian”, Portfolio to “Bundle” and Project to “Track |  |  | On Hold | Dev Team |  |  | TBD |  | Anu advised this would require an enhancement as it’s standard across the app and all accounts 12/05 Stuart: We can park this requirement for now
30 | MED | 3 | Hiscox | Days ago/Months ago – hide | Please hide this label. It is not relevant for client to know when we created the Chart or who created it. | Yes | On Hold | [5 empty] | Not able to implement this request as it would affect others accounts also.
31 | MED | 3 | Hiscox | Items/Charts list order | Last created items are appearing at first in Phone app. We need a way to change the sort order, so that important Charts can push to top. | Yes | On Hold | [5 empty] | As confirmed by Faris P. Mail has been attached in the TFS Task.
32 | MED | 3 | Hiscox | Chart created date – hide | Please hide the creation date of all Charts. This misleads customers thinking it is data updated date. (Replace with updated date) | Yes | Inprogress - IT4
33 | MED | 3 | Hiscox | Chart created user – hide | Please hide the user name who created the Chart. It is not relevant to client who designed/create the Chart. In our case, the Chart created user is not existing in the Project and this create confusion to Customer. | Yes | On Hold | [5 empty] | Not able to implement this request as it would affect others accounts also.
34 | MED | 3 | Hiscox | Chart - Show values against each bars | Please display the chart values against each bars. At present, user have to find it themselves by finding the corresponding value in X axis. | Yes | Completed
35 | MED | 3 | Hiscox | Portfolio tab – hide | Please hide this tab from the mobile app since we don’t have any Portfolio level user. | Yes | Waiting confirmation to Hold | Midhun |  |  |  |  | Need to analyse feasibility.
36 | MED | 3 | Hiscox | Default tab in user mobile app based on user type – Engagement Tab or Project Tab | In the user settings page, we need an option to set the default TAB for each user that they will see after logged into the Mobile App. | Yes | Completed | [5 empty] | Functionality was already available in the app.
37 | MED | 3 | Hiscox | Option to set a default page/chart for each user in user settings page | In the user settings page, we need an option to set the default page for each user that they will see after logged into the Mobile App. | Yes | Completed | EC Team |  |  |  |  | Marking as Completed as confirmed by Account POC. Email attached in TFS
38 | MED | 3 | Hiscox | "Invite" button in the User Management | "Invite" button in the User Management screen to send an invvite to new users to EdgeConnect App where they will be redirected to 'Password Reset' screen. | Yes | On Hold | [5 empty] | Out of scope, Currently when a new user is created, we are sending emails to the user which will redirect to the password reset page.
39 | MED | 3 | Hiscox | Welcoming New user in App | App should be able to identify if a username is new and redirect them to the Password Reset screen. | Yes | On Hold | [5 empty] | Out of scope as we are already sending welcome mail withpassword reset link when a new user is created.
44 | HIGH | 3 | Hiscox | Pie Chart: The values are to be presented in percentage. Please add % symbol along with the values. | Pie Chart: The values are to be presented in percentage. Please add % symbol along with the values. | Yes | Completed
45 | HIGH | 3 | Hiscox | Pie Chart: All Legends are not visible. | Pie Chart: All Legends are not visible. | Yes | On Hold | [5 empty] | All legends are visible in the details view of the chart.
46 | HIGH | 3 | Hiscox | Pie Chart: Data values are not displaying in the Chart. | Pie Chart: Data values are not displaying in the Chart. | Yes | On Hold | [5 empty] | Currently percentage is showing in the chart. Other data are showing as a legend.
47 | HIGH | 3 | Hiscox | Chart: Values in X-Axis are getting overlapped and unable to read | Chart: Values in X-Axis are getting overlapped and unable to read | Yes | Completed
48 | HIGH | 3 | Hiscox | Chart: Data value are not appearing along with the Chart data. | Chart: Data value are not appearing along with the Chart data. | Yes | Completed
40 | HIGH | 1 | JLT | increase the session time out as the user gets logged out easily | it would be really helpful if the time out was increased or when timed out, it would redirect to the login page automatically due to inactivity and not when an Update or Save button is clicked. |  | Completed
41 | MED | 2 | JLT | Please include the following options in the 'Status' drop down when creating or updating Milestones : 1. Awaiting Customer Sign Off 2. Yet to Start. | Certain items will be all set to begin and only awaitng a customer sign off or approval of some kind. It would be helpful if the customer was aware of this. |  | Completed-IT3/Inprogress - IT4
42 | MED | 2 | JLT | In Issues tab, please allow users to select more than one Milsestone (Multiselect) from “Select Milestones” drop down | An issue would be affecting more than one milestone simultaneously. Same would go for a Risk |  | Completed
43 | MED | 2 | JLT | In Issues tab please include the following 1. A drop down by name “Severity” with values as Critical, High, Medium, Low etc. 2. A text area with Name “Impact” |  |  | Completed
44 | HIGH | 2 | DEBENHAMS | The Risks and Milestone graphs /charts available in Webpage is not available in Andriod App. | This feature shoud be available in Mobile App for better visibility to customer. | Yes | Inprogress - IT5 | Bivin |  |  |  |  | Need to analyse feasibility.
45 | HIGH | 2 | DEBENHAMS | Text inside graph (eg pie chart) not available in Mobile version | This feature shoud be available in Mobile App for better understanding | Yes | On Hold | [5 empty] | In Pie charts values are showing as percentages as per the requirements from several account POCs from Europe BU itself. We are showing values in the pie chart legends also. (As per the Comments from Debenhams - 01/01/2018)
46 | HIGH | 2 | DEBENHAMS | Not able to create graphs with multiple parameters which is part ofour status reports. | Not able to create graphs with multiple parameters which is part of our status reports. | Yes | Inprogress - IT4 | [5 empty] | In progress
47 | MED | 2 | DEBENHAMS | Unable to find Archive Option | There should be an archive option visible to UST and customer to view old reports and data. | Yes | Inprogress - IT4 | Sooraj |  |  |  |  | Need to analyse feasibility.
48 | MED | 3 | DEBENHAMS | Days ago label in the right top corner of the page | Please hide this label as its not of importance to customer. | Yes | Inprogress - IT4 | [5 empty] | In Progress
49 | HIGH | 2 | DEBENHAMS | Last entered updates are appearing first in executive updates. | If we have to enter multiple texts , there should be an option to arrange them in the order of validity/relevance. | Yes | Planning IT5 | [5 empty] | DEBENHAMS POC Yet to Confirm.
50 | HIGH | 1 | DEBENHAMS | Portfolio Updates are not grouped in mobile application. | Portfolio updates shoud be grouped similar to that in web application. | Yes | Closed | [5 empty] | DEBENHAMS POC Yet to Confirm.
51 | HIGH | 2 | DEBENHAMS | Value population in Pie Chart in mobile application | Values are not expected to be populated in Pie chart. Still could see value getting populated for few. | Yes | On Hold | [5 empty] | In Pie charts values are showing as percentages as per the requirements from several account POCs from Europe BU itself. We are showing values in the pie chart legends also. (As per the Comments from Debenhams - 01/01/2018)
51 | HIGH | 1 | Harrods | RAG | Rag | Yes | Completed
52 |  |  | DEBENHAMS | Percentage calculation issue | The percentage split in one the pie charts is coming as 101 % instead of 100 % in Mobile application |  | Planning IT5
53 |  |  | Harrods | Consolidated - RAG | Our requirements on the RAG status is, we should have consolidated view of RAG status at the Enterprise and Portfolio. |  | Planning IT5
Note on B1: Stuart Saunders (UST, GBR): Impact to EdgeConnect roll out (High, Medium, Low)
Note on C1: Stuart Saunders (UST, GBR): Priority for release (High Priority = 1)
Note on E1: Stuart Saunders (UST, GBR): Clearly articulated requirement / issue
Note on H1: Stuart Saunders (UST, GBR): Development Status

## Security
# | Requirement | Status | Evidence (if applicable) | Comment
1 | Single tier containing the application & database | Closed | 10/05: HL design document shared and Anu reviewed and confirmed is satisfactory | Different servers are now being used for the application and the database. The database server is UST internal.
2 | No network or host based IDS/IPS within the environment or other network security monitoring by UST | Closed |  | 02/05 Stuart: Is the decision to accept the risk Experian's decision? If so, please confirm who and share any email trails with evidence 02/05 Anu: The estimated cost for implementing IDS/IPS was 9061USD for 3 yrs. This was communicated to both account team and Innovation team but not to Experian at the time. Stuart checking with account team 31/05 George :Complete - separate VM being stood up to install IPS. Network Design attached
3 | Logging & Monitoring – Full audit trails of user activity not yet available, this includes activity by UST within the application such as privileged user activity | Closed | 02/05: Sample report made available to Experian (Mike) 14/04. Assume is OK | All the activity is now captured in a report. 02/05 Stuart: Do we need to produce this ad hoc based on request or provide the report peridocially?
4 | User Authentication – password requirements not met | Closed |  | Password requirements are now as follows: 1. At least one capital letter and at least one small letter 2. At least one number 3. At least one special character 4. Minimum 8 characters 5. Last 13 passwords cannot be used 6. Password cannot contain the username
5 | User Registration – passwords to the systems sent via email | Closed |  | Emails are now sent for new user registration
6 | UST not leveraging Multi-Factor Authentication on Administrative Access to infrastructure supporting the application | Closed | 06/06: Architecture view / high level design document Shared | Multi-Factor Authentication now in place for Administrative Access to infrastructure supporting the application 02/05 Stuart: Architectural change - provide evidence through HL design document 03/05 Anu: HL design documentation requested 10/05: Some screen shots shared; checking with Gopa and Anu if this will suffice 11/05: Anu will explore further and see what was submitted to the change board 31/05: Complete - Multi-Factor Authentication now in place for Administrative Access to infrastructure supporting the application. Architecture view / high level design document Shared