## Pivot
Status | (Multiple Items)
Row Labels | Count of ID
Bug | 12
Feature | 3
Task | 21
Grand Total | 36

## Open Items
ID | Title | Type | Status | High | 1 | Comments | Account Source | Dev Effort Estimate | Owner | % | Start Date | End Date | Planned Release Date | RAGB | Next Steps/Comment | Comments From EC Dev Team
19146 | Mob_Members are repeating in group details page | Bug | Closed | High | 2 | Must Have | Not Available | 6 | Rohini
19300 | In mobile, legends of pie and donuts contain values and in web legends contain keys. Make it consistent | Bug | Closed | Medium | 4 | Good to Have | Not Available | 5
19335 | web_actual values in burn down chart is not a mandatory field | Bug | Closed | Low | 4 | Good to Have | Not Available | 2
19338 | web2_Issue in the given scenario: 1. Add an engagement to an admin (Only single engagement should be there) 2. Remove engagement 3. Tap on Manage admin 4. Tap on cancel button 5. It is showing New EU/Issue/Risk/Milestone count box 6. Tapping on any will show given error message. | Bug | Closed | Medium | 3 | Must Have | Not Available | 3 | Rohini | 100%
19363 | Mob_Not able to scroll organisations in hamburger menu if number of organisation is large | Bug | InProgress | Medium | 3 | Good to Have | Not Available | 2 | Libin
19376 | Web_Removed engagements are not removing from manage user page | Bug | Closed | Medium | 3 | Good to Have | Not Available | 16 | Rohini
19377 | Web2_Add a loader in manage user screen | Bug | Closed | Medium | 2 | Good to Have | Not Available | 2 | Rohini | 100%
19379 | Web2_Only admin user should be able to change the type of a user | Bug | Closed | High | 1 | Must Have | Not Available | 2 | Rohini | 100%
19382 | Web2_Duplicate values for engagement/Portfolio/project details in manage user screen | Bug | InProgress | High | 2 | Must Have | Not Available | 3 | Rohini
16573 | FeedBack viewing option in Web | Task | Closed | Low | 4 | Good to Have | Not Available | 8
17478 | Implement a Remember me feature in Login page | Task | Closed | Low | 3 | Good to Have | Not Available | 4
17500 | Instead of displaying the milestones in blocks, it would be more user friendly if they were as expandable lists. | Task | on Hold |  |  |  | Not Available | [8 empty] | Done as per design
18234 | Created/Updated date is showing wrong in mobile | Bug | Open | Medium |  | Must Have | Not Available | 2 | Rohini
18249 | No need to display UST owner name in NPS form. | Task | Closed | Medium | 3 | Good to Have | Not Available | 1 | IS
18250 | Change FY 2018 to FY 2017 in NPS | Task | Closed | Medium | 3 | Good to Have | Not Available | 2 | IS
18251 | No need to show engagement created date in NPS | Task | Closed | Medium | 3 | Good to Have | Not Available | 2 | IS
18252 | Show Engagement Name instead of UST Owner in NPS | Task | Closed | Medium | 3 | Good to Have | Not Available | 2 | IS
18253 | Change “Provide NPS” to “NPS Rating” | Bug | Open | Medium | 3 | Good to Have | Not Available | 1 | IS
18254 | Option to hide portfolio level in NPS | Bug | on Hold |  |  |  | Not Available | [8 empty] | Done as per design
18255 | NPS rating should be 1 to 10 in mobile | Bug | Closed | Medium | 3 | Good to Have | Not Available | 2 | IS
18280 | Portfolio grouping in transition projects | Task | Closed | Low | 3 | Good to Have | Not Available | 24
18281 | Cosmos DB integration | Task | on Hold |  |  |  | Not Available | [8 empty] | Not needed now
18283 | The negative axis for a bar graph is missing giving a wrong interpretation of data | Bug | Open | Medium | 2 | Must Have | Not Available | 8 | Legiesh
18284 | If data has been loaded for multiple months then viewing of data based on time period is not available | Task | InProgress | Low | 4 | Good to Have | Not Available | 24
19126 | executive updates with version management | Task | on Hold | Low | 4 | Good to Have | Not Available | [8 empty] | Duplicate 18284
19127 | include total count in the dashboard | Task | Closed | Medium | 3 | Good to Have | Not Available | 5 | IS
19182 | Pagination in mobile & Web | Task | InProgress | High | 2 | Must Have | Not Available | 80 | Vijesh | [6 empty] | Completed in Executive update Mobile.
19190 | Now the projects are sorted by last updated date, resulting in same project update in two different levels, ideally it should be grouped together. | Task | InProgress | Medium | 2 | Must Have | Not Available | 16 | Vijesh | 10% | [5 empty] | Group by projects sort by last updated time inside project
19191 | Need to increase the session timeout timeout duration. | Task | Closed | Low | 4 | Good to Have | Not Available | 1
19193 | Need to change Dashboard - change the count showing for New Executive Updates, New Issues, New Risks, New Milestones in to : 1/10 (no. of new / total ) format. | Task | on Hold |  |  |  | Not Available | [8 empty] | Duplicate 19127
19194 | Should have provision to change the chart type for the existing saved data – Instead of creating new chart. | Task | Open | Low | 3 | Good to Have | Not Available | 24
19195 | Value not displayed for Pie chart, Donut chart on the chart itself | Task | on Hold |  |  |  | Not Available | [8 empty] | Duplicate 19300
19196 | RAG (project health status) status at Executive level. | Task | Closed | High | 2 | Must Have | Not Available | 16 | IS
19197 | The negative axis for a bar graph is missing giving a wrong interpretation of data | Task | Closed |  |  |  | Not Available | [8 empty] | Duplicate18283
19198 | If data has been loaded for multiple months then viewing of data based on time period is not available | Task | Inprogress |  |  |  | Not Available | [8 empty] | Duplicate18283
19199 | While doing a pie chart , we now need to feed in percentages manually. | Task | Closed | Low | 3 | Good to Have | Not Available | 4 | IS | [6 empty] | Display percentage in Pie chart
19200 | Risks - We don’t have the required fields to show risks. Rather than title and description, we need relevant fields to talk about a risk. | Task | InProgress | Medium | 2 | Good to Have | Not Available |  | IS | [6 empty] | Need to confirm the required Fields
19201 | Notification feature when a new comment is added anywhere in the application | Task | InProgress | Medium | 3 | Good to Have | Not Available | 24
19202 | Can we indicate the number of open messages on the ICON of the app | Task | InProgress | Medium | 2 | Good to Have | Not Available | 40 | [7 empty] | Implement Push notification
19203 | Change Engagement header to “Experian”, Portfolio to “Bundle” and Project to “Track | Task | Invalid |  |  |  | Not Available | [8 empty] | Done as per design, common for all
19204 | Days ago/Months ago – hide: Please hide this label. It is not relevant for client to know when we created the Chart or who created it. | Task | Closed |  |  |  | Not Available | [8 empty] | Done as per design, common for all
19205 | Items/Charts list order: Last created items are appearing at first in Phone app. We need a way to change the sort order, so that important Charts can push to top. | Task | Closed |  |  |  | Not Available | [8 empty] | completed
19206 | Chart created date – hide: Please hide the creation date of all Charts. This misleads customers thinking it is data updated date. | Task | Closed |  |  |  | Not Available | [8 empty] | Done as per design
19207 | Chart created user – hide: Please hide the user name who created the Chart. It is not relevant to client who designed/create the Chart. In our case, the Chart created user is not existing in the Project and this create confusion to Customer. | Task | Invalid |  |  |  | Not Available | [8 empty] | Done as per design
19208 | Chart - Show values against each bars: Please display the chart values against each bars. At present, user have to find it themselves by finding the corresponding value in X axis. | Task | Open | Medium | 3 | Good to Have | Not Available | 16 | Legiesh | [6 empty] | Having some issues with mobile device width
19209 | Portfolio tab – hide: Please hide this tab from the mobile app since we don’t have any Portfolio level user. | Task | Invalid |  |  |  | Not Available | [8 empty] | Done as per design
19210 | Default tab in user mobile app based on user type – Engagement Tab or Project Tab: In the user settings page, we need an option to set the default TAB for each user that they will see after logged into the Mobile App. | Task | Closed |  |  |  | Not Available | [8 empty] | Tabs will be available to the user based on acces level.
19211 | Option to set a default page/chart for each user in user settings page: In the user settings page, we need an option to set the default page for each user that they will see after logged into the Mobile App. | Task | invalid | Low | 5 | Good to Have | Not Available | 24
19212 | "Invite" button in the User Management: "Invite" button in the User Management screen to send an invvite to new users to EdgeConnect App where they will be redirected to 'Password Reset' screen. | Task | Closed |  |  |  | Not Available | [8 empty] | Currenltly have an option to add user from manage user screen.
19213 | Welcoming New user in App: App should be able to identify if a username is new and redirect them to the Password Reset screen. | Task | Closed |  |  |  | Not Available | [8 empty] | Completed
10024 | ECQA_Add an option to edit / delete comment | Feature | InProgress | Medium | 4 | Good to Have | Not Available | 16
19054 | Mob_Add edit/delete menu option for executive update | Feature | on Hold |  |  |  | Not Available | [8 empty] | Done as per design, having limitation in mobile
19380 | Web2_Show Engagements of 'Manage Admin' in alphabetical order | Feature | Closed | Medium | 3 | Must Have | Not Available | 4
19381 | Mob_Show attached Issue/Risk/Milestone as hyperlinks | Feature | Closed | Low | 4 | Good to Have | Not Available | 2 | [7 empty] | Functionality exist, need to add some style only
19383 | web2_Add validation to Update version | Feature | Closed |  |  |  | Not Available | [8 empty] | Done as per design
| If values for multiple months are given in a bar graph, while viewing in mobile device, the spacing between the graph is considerably big and the user has to scroll multiple times just to view 6 months of data | Feature | Open |  |  |  | Schroders
| Tool tips need to be added for fields, o e.g.: there are different fields for title, Highlight title etc. for bar chart, but what is the significance or difference is not understood. Create User panel also has Name, username etc. | Feature | Closed |  |  |  | Hermes | [8 empty] | Added tooltip for title, rest all the details can be found in detail page, as per design
| Bar Chart – Currently we can enter only 3 values #Total TCs, #Passed & #Failed and the other values like Not Run, Blocked, In Progress cannot be entered. (sample below 1st image). | Feature | InProgress | Medium | 3 |  | Harrods | 16 | [7 empty] | To be discussed
| Risks - We don’t have the required fields to show risks. Rather than title and description, we need relevant fields to talk about a risk. Optimust screenshot here. Not every detail may be required, but basic risk elements need to be there. These business requirements should be coming to Edge Connect team from SEPG to make this tool more effective. | Feature | on Hold | [12 empty] | Duplicate 19200
| The updated date is showing up wrong in the mobile view. The create date is shown instead. | Feature | Closed | [12 empty] | Duplicate 18234
| I could not draw the control limit lines and the call out. (red marked oval call out) - Team (Image update can be used) | Feature | on Hold | Medium | 3 | Good to Have | Hermes | [8 empty] | Bar chart with line chart option is available now.
| Pie Chart: All Legends are not visible. | Feature | Closed |  |  |  | Hiscox | [8 empty] | In listing restricted to 2 in listing, details page shows all values.
| Pie Chart: Data values are not displaying in the Chart. | Feature | Closed |  |  |  | Hiscox | [8 empty] | Done as per design
| Chart: Values in X-Axis are getting overlapped and unable to read | Feature | Open | Medium | 3 | Good to Have | Hiscox | 8 | Legiesh
| Please include the following options in the 'Status' drop down when creating or updating Milestones : 1. Awaiting Customer Sign Off (Awaiting Sign Off) 2. Yet to Start.(Not needed) | Feature | Open | Medium | 3 | Good to Have | JLT | 8 | Libin
| In Issues tab, please allow users to select more than one Milsestone (Multiselect) from “Select Milestones” drop down | Feature | Open | Medium | 3 | Good to Have | JLT | 16 | Libin | [6 empty] | Done as per design
| In Issues tab please include the following 1. A drop down by name “Severity” with values as Critical, High, Medium, Low etc. 2. A text area with Name “Impact” | Feature | Open | Medium | 3 | Good to Have | JLT | 16 | Rohini
| The Risks and Milestone graphs /charts available in Webpage is not available in Andriod App. | Feature | on Hold | Low | 4 | Good to Have | DEBENHAMS | 40 | [7 empty] | Done as per design
| Not able to create graphs with multiple parameters which is part of our status reports. | Feature | Closed |  |  |  | DEBENHAMS | [8 empty] | To be discussed
19471 | Executive Update drill down | Feature | Closed | High | 1 | Must Have |  | 40 | Libin | 80% | [5 empty] | Web Completed . Mobile final changes in progress
| Executive Summary | Feature | Closed | High | 1 | Must Have |  | 32 | Legiesh
| Image upload size correction for web and Mobile | Bug | Closed | High | 1 | Must Have |  | 12 | Legiesh
| Increase the login session time | Feature | Closed | High | 1 | Must Have
| Decimals are not allowed on the chart values | Bug | Closed | High |  | Must Have
| Save Button not enabling while adding milestone. | Bug | Closed | High |  | Must Have
| Color picker for charts | Feature | Open | High | 1 | Good to Have | Team | 40 | Legiesh
| Push notification | Feature | Open | High |  | Good to Have | Team |  | Vijesh

## List
Comments | Impact | Priority
Critical Issue | High | 1
Must Have | Medium | 2
Good to Have | Low | 3
4
5

## Task_Not In Use
ID | Title
16573 | FeedBack viewing option in Web
16779 | Global Monitoring
17478 | Implement a Remember me feature in Login page
17484 | It will be good to have a check box or can we enable voice recognition or something to login
17500 | Instead of displaying the milestones in blocks, it would be more user friendly if they were as expandable lists.
18234 | Created/Updated date is showing wrong in mobile
18249 | No need to display UST owner name in NPS form.
18250 | Change FY 2018 to FY 2017 in NPS
18251 | No need to show engagement created date in NPS
18252 | Show Engagement Name instead of UST Owner in NPS
18253 | Change “Provide NPS” to “NPS Rating”
18254 | Option to hide portfolio level in NPS
18255 | NPS rating should be 1 to 10 in mobile
18280 | Portfolio grouping in transition projects
18281 | Cosmos DB integration
18283 | The negative axis for a bar graph is missing giving a wrong interpretation of data
18284 | If data has been loaded for multiple months then viewing of data based on time period is not available
19126 | executive updates with version management
19127 | include total count in the dashboard
19182 | Pagination
19190 | Now the projects are sorted by last updated date, resulting in same project update in two different levels, ideally it should be grouped together.
19191 | Need to increase the session timeout timeout duration.
19193 | Need to change Dashboard - change the count showing for New Executive Updates, New Issues, New Risks, New Milestones in to : 1/10 (no. of new / total ) format.
19194 | Should have provision to change the chart type for the existing saved data – Instead of creating new chart.
19195 | Value not displayed for Pie chart, Donut chart on the chart itself
19196 | RAG (project health status) status at Executive level.
19197 | The negative axis for a bar graph is missing giving a wrong interpretation of data
19198 | If data has been loaded for multiple months then viewing of data based on time period is not available
19199 | While doing a pie chart , we now need to feed in percentages manually.
19200 | Risks - We don’t have the required fields to show risks. Rather than title and description, we need relevant fields to talk about a risk.
19201 | Notification feature when a new comment is added anywhere in the application
19202 | Can we indicate the number of open messages on the ICON of the app
19203 | Change Engagement header to “Experian”, Portfolio to “Bundle” and Project to “Track
19204 | Days ago/Months ago – hide: Please hide this label. It is not relevant for client to know when we created the Chart or who created it.
19205 | Items/Charts list order: Last created items are appearing at first in Phone app. We need a way to change the sort order, so that important Charts can push to top.
19206 | Chart created date – hide: Please hide the creation date of all Charts. This misleads customers thinking it is data updated date.
19207 | Chart created user – hide: Please hide the user name who created the Chart. It is not relevant to client who designed/create the Chart. In our case, the Chart created user is not existing in the Project and this create confusion to Customer.
19208 | Chart - Show values against each bars: Please display the chart values against each bars. At present, user have to find it themselves by finding the corresponding value in X axis.
19209 | Portfolio tab – hide: Please hide this tab from the mobile app since we don’t have any Portfolio level user.
19210 | Default tab in user mobile app based on user type – Engagement Tab or Project Tab: In the user settings page, we need an option to set the default TAB for each user that they will see after logged into the Mobile App.
19211 | Option to set a default page/chart for each user in user settings page: In the user settings page, we need an option to set the default page for each user that they will see after logged into the Mobile App.
19212 | "Invite" button in the User Management: "Invite" button in the User Management screen to send an invvite to new users to EdgeConnect App where they will be redirected to 'Password Reset' screen.
19213 | Welcoming New user in App: App should be able to identify if a username is new and redirect them to the Password Reset screen.

## Features_Not In Use
ID | Title
10024 | ECQA_Add an option to edit / delete comment
19054 | Mob_Add edit/delete menu option for executive update
19380 | Web2_Show Engagements of 'Manage Admin' in alphabetical order
19381 | Mob_Show attached Issue/Risk/Milestone as hyperlinks
19383 | web2_Add validation to Update version